## PLCF Responsibility Matrix
LEGEND: P = Primary Responsibility O = Task Owner C = Consultant A = Approval
Task | XYZ Business Unit | XYZ CRE/FM | Design Professionals | Construction Manager | General Contractor | Other | Comment
Project Initiation
Submit Project Requirement to FM CRE/FM | O
Task facility requirements and funding | O,P | C
Prepare Design SOW |  | O
Select Design Consultant |  | O
Prepare Design Consultant Task Order |  | O
Select Construction Manager |  | O
Prepare Const Mgr Task Order |  | O
Site Selection and Lease
Task Real Estate Transactions to initiate site search | A | O,P
Task Leasing Agent to Search | A | O
Review preliminary list | C | O,P
Task short list search |  | O,P
Select Site | C | O,P
Preliminary Design Phase
Pre-Design Meeting; minutes, set schedule | C | O | C | P
Prepare Project Directory |  | O |  | P
Cost Control System |  | O |  | P
Schedule Control System |  | O |  | P
Program Management Information System |  | O |  | P
Correspondence Control System |  | O |  | P
Weekly Progress and Budget Status Report |  | O |  | P |  |  | Weekly mtgs intended for FM CRE/FM, A/E and CM
Develop a Project Action Plan |  | O |  | P
Develop Project Program | C | O | P | C
Obtain Preliminary Project Data; Site & Building survey, borings, as-built drawings, etc. |  | O | P
Apply for & track all Regulatory Permits |  | O | P
Schematic and DD Phases
Confirm Availability of: |  | O | P
Sanitary Service
Storm Water
Domestic Water
Gas Service
Fire Service
Electric Service
Telephone Service | [6 empty] | FM ESM to Assist
Security Service | [6 empty] | FM Security to Assist
Prepare Construction Cost Estimate |  | O | C | P
Maintain / Update Design Schedule |  | O | P | C
Provide Info on Fannie Mae purchased Equipment |  | O | P | C
Prepare & Submit Initial Budget/Schedule |  | O | C | C
Review Initial Budget / Schedule, consolidate & resolve all comments |  | O | C | P
Approve site and Initial Budget/Schedule | A | O
Identify Long Lead Items, prepare orders |  | O | C | P
Prepare & Submit 50% Design |  | O | P | C
Review/Approve 50% Design |  | O | P
Order Long Lead Items |  | O | C | P
70 % Design Document Phase
Determine Contracts to be Awarded |  | O,P | C | C
Prepare 70% Plans |  | O | P
Prepare Specifications Outline |  | O | P
Prepare Structural Calculations |  | O | P
Prepare HVAC Cal & Narrative |  | O | P
Submit 70 % Documents |  | O | P
Review 70% Documents, submit comments | C | A | P | C
Review submittals, shop dwg. requirements list |  | O | P | A
Consolidate comments; send to DP |  | O |  | P
Review & Approve 70 % Documents | C | O | P
Update Design Schedule | C | O | P | C
Submit Design for Building Permit Review |  | O | P
95 % Design Submittal Phase
Obtain Code Review Approval |  | O | P |  |  | Code official
Submit Design Drawings |  | O | P
Submit Specifications |  | O | P
Submit Draft Contract and all attachments |  | O | P
Review Documents, compile, and submit final comments | C | O | C | P
Review & Approve 95 % Documents | C | O |  | P
Review Plans for Constructability, & Criteria |  | O |  | P
Value Engineer Project |  | O |  | P
Develop General Contractor Bid List | C | O | C | P
Resolve and incorporate All Comments |  | O | P
Prepare Bid Documents, 100% |  | O | P | C
Track All Permits |  | O | P | C
Track All Project Documents |  | O | C | P
Presentations at Public Hearings |  | O | P | C
Evaluate A/E Performance |  | O |  | P
Evaluate A/E Invoices |  | O |  | P
Authorize A/E Invoice payment |  | O
Approve CM Invoices |  | O
Maintain Financial Tracking |  | O |  | P
Bid / Award Phase
Submit Bid Documents to FM Sourcing |  | O | P | C
Review & approve bid documents |  | O,P |  |  |  | FM Sourcing
Distribute Bid Documents |  | O |  | P
Pre-Bid Conference |  | O |  | P
Prepare & Distribute Minutes |  | O |  | P
Attend Pre-Bid Conference | C | O | C | P | C | C
Prepare Addenda |  | O | P | A
Review & approve addenda |  | O | P | C |  | FM Sourcing
Publish and Issue Addenda |  | O | P |  |  | FM Sourcing
Schedule & Coordinate Bid Openings |  | O |  | C |  | FM Sourcing
Receive, Open & Record Bids |  | O |  | C |  | FM Sourcing
Review Bids and Provide Cost Analysis |  | O |  | C
Review & approve Sub-Contractors |  | O |  | P
Determination of Award | C | O |  | P
Prepare Contracts - Validate Blanket Agreements |  | O |  | C
Sign Contracts |  | O |  | C |  | P, FM Sourcing
Distribute Signed Contracts |  | O |  | C |  | P, FM Sourcing
Issue notice to proceed |  | O |  | C |  | P, FM Sourcing
Prepare Design Consultant Performance Evaluation |  | O |  | P
Construction Administration Phase
Approve Contractor’s Schedule | C | O | C | P | C
Review/Approve Contractor Schedule of Values Breakdown |  | O | C | P
Pre-Construction Meeting | C | O | C | P | C
Manage RFI process | C | O | C | P | C
Submit Change Request | C | O | C | C | P
Evaluate/Negotiate/Recommend Change Request |  | O | C | P | C
Change Orders | C | O |  | P
Track & Distribute Documents |  | O |  | P
Review/Approve submittals |  | O | P | C
Approve Shop Drawings |  | O | P | C
Approve Test Reports |  | O | P | C
Prepare Change Request Plans & Specs |  | O | P | C
Weekly Project Progress Meetings |  | O | C | P | C |  | A and E Disciplines req'd at weekly Progress Mtgs.
Review Contractor’s Progress Schedule |  | O |  | P | C
Evaluate / Recommend Contractor Invoices |  | O | C | P
Field inspections |  | O | C | P
Meeting Minutes and Budget Status Reports |  | O |  | P
Submit Daily Field Reports |  | O |  | A | P
Construction Photographs |  | O |  | P/C | P/C
Prepare “As-Built” Plans |  | O |  | C | P
Prepare O&M Manuals |  | O |  | C | P
Coordinate Substantial Completion |  | O | C | P
Substantial completion certificate |  | O | C | P
Project Close Out Phase
Conduct prefinal inspection |  | O | P | C | C
Prepare / consolidate Punchlist(s) |  | O | P | C
Coordinate Code Inspection |  | O |  | C | P
Complete Punchlist Items |  | O |  | C | P
Verify Completion of Punchlist Items |  | O | P | C
Plan, Schedule & Control Final Inspection by All Parties Incl. Regulatory Agencies |  | O | C | C/P | P/C
Site commissioning | C | O | C | C | P
Coordinate Equipment Operation Training |  | O |  | P
Provide Maintenance & Operating Manuals |  | O | C | C | P
Provide All Guarantees & Reports |  | O |  | A | P
Assemble & approve Close-Out Documents |  | O |  | P | C
Evaluate As-Built Plans |  | O | C | P
Prepare Record Set Drawings |  | O | P |  | C
Sign “Certificate Of Final Completion |  | O | P | A
Close-Out Design Consultant's Contract |  | O |  | C
Final Contract Acceptance |  | O |  | P
All Permit closeouts |  | O |  | A | P
Occupancy certificate |  | O |  | A | P
Post Occupancy Phase
Provide Post-Occupancy Assistance |  | O |  | C
Correct Warranty Issues |  | O |  | A | P
Update FM Design Standards |  | O | P | C
Lessons Learned |  | O,P | C | C | C | C