## Using This Tool
Introduction
The PMO/Portfolio Management Software Evaluation tool has been developed to support organizations in evaluating and selecting a portfolio management tool that is appropriate for their organization. We have developed the tool to provide a comprehensive set of dimensions. These dimensions represent the attributes that organizations should take into consideration when selecting a portfolio management software package for their purposes.
The PMO/Portfolio Management Software Evaluation tool has been designed to be flexible and responsive to the needs of your organization. It can be expanded to include additional dimensions that are also relevant to your organization, and enables you to define the specific criteria you are looking for.
Deciding What Is Important
The development of the PMO/Portfolio Management Software Evaluation tool involved identifying the relevant dimensions for evaluating portfolio management tools. The approach we took as an exhaustive one, and is based upon both our familiarity with the tools in the marketplace and what organizations really look for once they start to actually use them. That said, not all of the criteria are going to be relevant for all organizations. While we have attempted to be as complete as possible, it’s up to you to decide what is truly important for your organization. Out of the criteria that have been identified, what defines portfolio management to your organization and what do you need to see in a portfolio management package that will support this process? Focus on these criteria first and foremost. If additional criteria also appear to offer value, by all means include them – but don’t be afraid to delete criteria where you don’t see them as being necessary.
Using The Tool
In using the PMO/Portfolio Management Software Evaluation tool, use the following steps to guide you in setting up your evaluation process and selecting the tool that is most appropriate for your needs.
1. Identify the software packages that you will be evaluating. List these along the top row of the Tool (spreadsheet).
2. Review the dimensions defined within the evaluation spreadsheet. For each dimension:
Identify the importance of the dimension to your organization, using the following scale:
- Function is essential; failure to receive the capability would mean the solution is unusable.(5 points)
- Function is highly desired; not meeting the criteria would require costly workarounds to accommodate. (4 points)
- Function is very desired; not meeting the criteria means that some extra work would be created. (3 points)
- Function is important; it would be inconvenient not to have the criteria met. (2 points)
- Function is unimportant (1 point)
3. For each of the scoring criteria, the maximum possible score for that section is automatically calculated for each category.
4. Define the specific criteria that must be met to support the dimension. Examples could include:
Dimensions 1.1.1 – Ability to identify opportunities:
Criteria: Require ability to capture the request, who requested it, the degree of importance and the date the request should be completed by.
Dimension 2.1 – Accounting integration:
Criteria: Automatically generate initial budgets based upon project plan; automatically update budget forecasts based on progress estimates; automatically import actual costs from accounting system.
Dimension 7.1 – Operating System:
Criteria: Windows XP Service Pack 2
Note the scoring built into the spreadsheet. Each tool is ranked on a 1-5 scale, based upon the following criteria.
o Criteria are completely met (5 points)
o Criteria are mostly met; requirement can be delivered by the solution in its current form (4 points)
o Criteria partially met; requirement can be met with some changes to business processes (3 points)
o Criteria not met; requirement can be met with software customization (2 points)
o Criteria not met (1 point)
5. Score each solution against your defined criteria in the ‘Evaluation’ column of the spreadsheet. As you score each software package, a composite score is calculated in the ‘Analysis’ section.
The composite score is the product of the Importance for that dimension multiplied by the Evaluation for that dimension.
o Totals are provided in the Analysis section for each category.
o Overall totals are calculated at the bottom of the spreadsheet.

## PMO Software Evaluation Model
PMO/Portfolio Management Software Evaluation Model |  |  | Traffic Light Legend: Green: 0% to 15% Yellow: 16% to 24% Red: 25+% |  |  |  |  | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0
Evaluation Metrics |  |  | Evaluation |  |  |  |  | Analysis
Dimension | Importance (1-5) | Criteria | Tool #1 | Tool #2 | Tool #3 | Tool #4 | Tool #5 | Tool #1 | Tool #2 | Tool #3 | Tool #4 | Tool #5
1 Functions | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 Opportunity Identification/Demand Management | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 Identification | [7 empty] | 0 | 0 | 0 | 0 | 0
1.1.2 Identify follow-up information requirements | [7 empty] | 0 | 0 | 0 | 0 | 0
1.1.3 Evaluation | [7 empty] | 0 | 0 | 0 | 0 | 0
1.2 Portfolio Identification | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1 Organizational | [7 empty] | 0 | 0 | 0 | 0 | 0
1.2.2 Product-based | [7 empty] | 0 | 0 | 0 | 0 | 0
1.2.3 Strategy-based | [7 empty] | 0 | 0 | 0 | 0 | 0
1.2.4 Project type | [7 empty] | 0 | 0 | 0 | 0 | 0
1.3 Project Prioritization & Selection | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3.1 Criteria development | [7 empty] | 0 | 0 | 0 | 0 | 0
1.3.2 Scoring and evaluation | [7 empty] | 0 | 0 | 0 | 0 | 0
1.3.3 Prioritization and ranking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.3.4 Project approvals | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4 Resource Management | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4.1 Resource identification | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.2 Resource skill definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.3 Skill-based resource searches | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.4 Role-based resource searches | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.5 Resource capacity management | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.6 Assignments to specific individuals | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.7 Role-based assignments | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.8 Department/group assignments | [7 empty] | 0 | 0 | 0 | 0 | 0
1.4.9 Management of 100% of resource effort | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5 Governance | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5.1 Governance role identification | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.2 Governance process definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.3 Gating process definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.4 Process-based milestone definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.5 Project-based milestone definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.6 Approval tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.7 Approval workflow | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.8 Electronic approval/signatures | [7 empty] | 0 | 0 | 0 | 0 | 0
1.5.9 Follow-up tracking and management | [7 empty] | 0 | 0 | 0 | 0 | 0
1.6 Methodology Support | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6.1 Methodology definition support | [7 empty] | 0 | 0 | 0 | 0 | 0
1.6.2 Support for multiple methodologies | [7 empty] | 0 | 0 | 0 | 0 | 0
1.6.3 Methodology adaptation for individual projects | [7 empty] | 0 | 0 | 0 | 0 | 0
1.6.4 Template definition and distribution | [7 empty] | 0 | 0 | 0 | 0 | 0
1.6.5 Standard organization definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.6.6 Role and responsibility definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7 Workflow | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7.1 Standard workflow definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7.2 Multiple workflow definition support | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7.3 Workflow customization for individual projects/portfolios | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7.4 Management of individual approvals | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7.5 Management of multiple/group approvals | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7.6 Support for different approval thresholds | [7 empty] | 0 | 0 | 0 | 0 | 0
1.7.7 Approval/role delegation | [7 empty] | 0 | 0 | 0 | 0 | 0
1.8 Document Management | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8.1 Project documentation archiving | [7 empty] | 0 | 0 | 0 | 0 | 0
1.8.2 Project deliverable archiving | [7 empty] | 0 | 0 | 0 | 0 | 0
1.8.3 Support for multiple document types | [7 empty] | 0 | 0 | 0 | 0 | 0
1.8.4 Customizable document metadata | [7 empty] | 0 | 0 | 0 | 0 | 0
1.8.5 Support for multiple project categories/portfolios | [7 empty] | 0 | 0 | 0 | 0 | 0
1.8.6 Full-text document search and retrieval | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9 Project Management | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.9.1 Project plan definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.2 Business case definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.3 Risk Tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.4 Risk monitoring and management | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.5 Issue tracking and management | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.6 Scope change identification | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.7 Scope change impact analysis | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.8 Scope change approval | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.9 Baseline management | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.10 Cost tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.11 Effort tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.12 Schedule tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.13 Performance measurement | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.14 Resource assignment monitoring | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.15 Resource levelling | [7 empty] | 0 | 0 | 0 | 0 | 0
1.9.16 Lessons learned/post implementation reviews | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10 Reporting | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.10.1 Project reporting | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.2 Portfolio reporting | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.3 Role-based reporting | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.4 Standard project management reports | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.5 Standard portfolio reports | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.6 Dashboard portfolio views | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.7 Dashboard project views | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.8 Drill-down from dashboards to individual documents/deliverables | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.9 Customization of reports | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.10 Customization of dashboards | [7 empty] | 0 | 0 | 0 | 0 | 0
1.10.11 Personalized reports/dashboards | [7 empty] | 0 | 0 | 0 | 0 | 0
1.11 Analysis | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.11.1 Analytical tools | [7 empty] | 0 | 0 | 0 | 0 | 0
1.11.2 Decisions support tools | [7 empty] | 0 | 0 | 0 | 0 | 0
1.11.3 Statistical and trend analysis tools | [7 empty] | 0 | 0 | 0 | 0 | 0
1.12 Value Realization | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.12.1 Business case definition | [7 empty] | 0 | 0 | 0 | 0 | 0
1.12.2 Business case change management | [7 empty] | 0 | 0 | 0 | 0 | 0
1.12.3 Performance measurement tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
1.12.4 Value realization management | [7 empty] | 0 | 0 | 0 | 0 | 0
2 Integration | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 Accounting | [7 empty] | 0 | 0 | 0 | 0 | 0
2.2 HR systems | [7 empty] | 0 | 0 | 0 | 0 | 0
2.3 Payroll systems | [7 empty] | 0 | 0 | 0 | 0 | 0
2.4 Work management systems | [7 empty] | 0 | 0 | 0 | 0 | 0
2.5 Business planning | [7 empty] | 0 | 0 | 0 | 0 | 0
2.6 Project management software | [7 empty] | 0 | 0 | 0 | 0 | 0
2.7 Time reporting | [7 empty] | 0 | 0 | 0 | 0 | 0
2.8 Analytics engines | [7 empty] | 0 | 0 | 0 | 0 | 0
2.9 Dashboard reporting | [7 empty] | 0 | 0 | 0 | 0 | 0
2.10 E-mail | [7 empty] | 0 | 0 | 0 | 0 | 0
2.11 Custom interface capability | [7 empty] | 0 | 0 | 0 | 0 | 0
2.12 XML support | [7 empty] | 0 | 0 | 0 | 0 | 0
3 Standards Support | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 ISO 9000 | [7 empty] | 0 | 0 | 0 | 0 | 0
3.2 ITIL | [7 empty] | 0 | 0 | 0 | 0 | 0
3.3 Sarbanes-Oxley | [7 empty] | 0 | 0 | 0 | 0 | 0
3.4 CMMI | [7 empty] | 0 | 0 | 0 | 0 | 0
3.5 PMBOK | [7 empty] | 0 | 0 | 0 | 0 | 0
4 Vendor | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 Stability | [7 empty] | 0 | 0 | 0 | 0 | 0
4.2 Revenue | [7 empty] | 0 | 0 | 0 | 0 | 0
4.3 Installed base | [7 empty] | 0 | 0 | 0 | 0 | 0
4.4 Partners | [7 empty] | 0 | 0 | 0 | 0 | 0
4.5 Support policies | [7 empty] | 0 | 0 | 0 | 0 | 0
4.6 Warranty | [7 empty] | 0 | 0 | 0 | 0 | 0
4.7 Consulting Support | [7 empty] | 0 | 0 | 0 | 0 | 0
4.8 Customization services | [7 empty] | 0 | 0 | 0 | 0 | 0
4.9 Implementation services | [7 empty] | 0 | 0 | 0 | 0 | 0
4.10 Training services | [7 empty] | 0 | 0 | 0 | 0 | 0
4.11 After-sales support and care | [7 empty] | 0 | 0 | 0 | 0 | 0
4.12 Escrow policy | [7 empty] | 0 | 0 | 0 | 0 | 0
5 Customization | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 Methodology | [7 empty] | 0 | 0 | 0 | 0 | 0
5.2 Templates | [7 empty] | 0 | 0 | 0 | 0 | 0
5.3 Organization Structure | [7 empty] | 0 | 0 | 0 | 0 | 0
5.4 Project Structure | [7 empty] | 0 | 0 | 0 | 0 | 0
5.5 Project Evaluation Criteria | [7 empty] | 0 | 0 | 0 | 0 | 0
5.6 Project Planning Requirements | [7 empty] | 0 | 0 | 0 | 0 | 0
5.7 Project Tracking | [7 empty] | 0 | 0 | 0 | 0 | 0
5.8 Project Reporting | [7 empty] | 0 | 0 | 0 | 0 | 0
5.9 Project Metrics | [7 empty] | 0 | 0 | 0 | 0 | 0
6 Administration | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 Organizational Definition | [7 empty] | 0 | 0 | 0 | 0 | 0
6.2 Role Definition | [7 empty] | 0 | 0 | 0 | 0 | 0
6.3 Category Definition | [7 empty] | 0 | 0 | 0 | 0 | 0
6.4 Multiple time zones | [7 empty] | 0 | 0 | 0 | 0 | 0
6.5 Multiple currencies | [7 empty] | 0 | 0 | 0 | 0 | 0
6.6 Functional Security | [7 empty] | 0 | 0 | 0 | 0 | 0
6.7 Project Security | [7 empty] | 0 | 0 | 0 | 0 | 0
6.8 Data Security | [7 empty] | 0 | 0 | 0 | 0 | 0
6.9 Role-Based Security | [7 empty] | 0 | 0 | 0 | 0 | 0
6.10 Person-Based Security | [7 empty] | 0 | 0 | 0 | 0 | 0
6.11 Role Delegation | [7 empty] | 0 | 0 | 0 | 0 | 0
6.12 Audit trails | [7 empty] | 0 | 0 | 0 | 0 | 0
6.13 Archiving | [7 empty] | 0 | 0 | 0 | 0 | 0
7 Technology Environment | 0 | < Maximum Score | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1 Operating System | [7 empty] | 0 | 0 | 0 | 0 | 0
7.2 Database | [7 empty] | 0 | 0 | 0 | 0 | 0
7.3 Delivery Platform | [7 empty] | 0 | 0 | 0 | 0 | 0
| 0 | <<< Maximum Possible Score | [5 empty] | 0 | 0 | 0 | 0 | 0
Note on B8: Identification - What information needs to be defined for opportunities as they are identified? - How should opportunities be submitted? - Who should be responsible for receiving and reviewing opportunity requests?
Note on B9: Identify follow-up information requirements - How should requests for follow-up information and clarification be handled? - How do opportunities need to be tracked when additional information is being sought?
Note on B10: Evaluation - How do opportunity requests get evaluated? - What criteria is required? - Who is responsible for evaluation of requests? - What happens if a request is not initially approved?
Note on B12: Organizational - What portfolios are required based upon the organizational structure? - Is there a hierarchy of portfolios required?
Note on B13: Product-based - What portfolios are required based upon specific products, services or customer groups? - Is there a hierarchy of portfolios required?
Note on B14: Strategy-based - What portfolios are required to track the attainment of organizational strategies? - Are there hierarchies of portfolios required?
Note on B15: Project Type - What portfolios are required for project types? - Are there hierarchies of portfolios required?
Note on B17: Criteria Development - What capabilities are required to develop prioritization criteria? - What types of criteria will be utilized? - Will different criteria be used for different portfolios and project types?
Note on B18: Scoring and Evaluation - How are scores developed and projects evaluated? - Is this a confidential process or a public process? - Who is involved in scoring project opportunities? - What kinds of scorecards or criteria will be used?
Note on B19: Prioritization and Ranking - What is the prioritization process for the organization? - How will ranking and selection be performed? - Is this done for all projects together, or subdivided by organization, project type, customer or other portfolio segments? - How are thresholds determined for which projects will and won’t proceed? - How are new requests managed?
Note on B20: Project Approvals - What is the approval process for projects as they are prioritized? - Who is involved in the process? - What steps are required? - Are there different steps for different portfolios? - What information needs to be tracked about project approvals?
Note on B22: Resource Identification - What information needs to be captured about individual resources? - What resources will be included within the system? - Are resources defined based upon organizational groupings, resource pools or other means of segmentation?
Note on B23: Resource Skill Definition - What skill information is required? - How should skills be defined? - What information about skills will be required? - To what level of detail? - Are there different groupings or hierarchies of skill that should be maintained?
Note on B24: Skill-based Resource Searches - How will information about available resources be identified when searching for people with specific skills? - What criteria would be used? - What information should be returned?
Note on B25: Role-based Resource Searches - How will role-based searches for resources be managed? - What criteria should be used? - What information should be returned?
Note on B26: Resource Capacity Management - How should allocations and resource availability be managed? - Who is responsible for managing resource assignments and allocations? - What restrictions should be in place on who can assign resources to projects? - What are the steps required to secure an assignment?
Note on B27: Assignments to Specific Individuals - How are assignments to individually identified resources managed? - What information should be required? - What are the approval steps required to assign a specific person?
Note on B28: Role-based Assignments - How should assignments to a role or resource pool be managed? - What process is required? - What are the approval steps required to assign to a role group?
Note on B29: Department/Group Assignments - How are department or group assignments managed? - What are the steps required? - How do department assignments get further assigned to specific people? - How do people within a group review and select their assignments?
Note on B30: Management of 100% of Resource Effort - To what extent does 100% of resource effort need to be managed? - Will operational and administrative allocations be managed, as well as project assignments? - How do these allocations need to be managed?
Note on B32: Governance Role Identification - What are the governance roles that need to be assigned? - How does this information need to be presented?
Note on B33: Governance Process Definition - How does the governance process need to be defined and managed? - What information is available? - How much does this process need to be automated?
Note on B34: Gating Process Definition - How does the gating process need to be defined and managed? - What information is available? - How much does this process need to be automated? A stage-gate model is a technique in which a (product, process, system) development process is divided into stages separated by gates. At each gate, the continuation of the development process is decided by (typically) a manager or a steering committee. The decision is based on the information available at the time, including e.g. business case, risk analysis, availability of necessary resources (money, people with correct competencies) etc. The stage-gate model may also be known as stage-limited commitment or creeping commitment.Gates provide various points during the process where an assessment of the quality of an idea is undertaken. It includes three main issues: * Quality of execution: Checks whether the previous step is executed in a quality fashion. * Business rationale: Does the project continue to look like an attractive idea from an economic and business perspective. * Action plan: The proposed action plan and the requested resources reasonable and sound. A gate meeting can lead to four results: go, kill, hold, recycle. Gates have a common structure and consist of three main elements: Deliverables, Criteria and Outputs. * Deliverables: What the project manager and team deliver to the decision point.These deliverables are decided at the output of the previous gate,and are based on a standard menu of deliverables for each gate. * Criteria: Questions or metrics on which the project is judged in order to make the Go/Kill/Hold/Recycle and prioritization decision. * Outputs: Results of the gate review -a decision (Go/Kill/Hold/Recycle),along with an approved action plan for the next gate, and a list of deliverables and date for the next gate.
Note on B35: Process-based Milestone Definition - What process-based milestones need to be defined? - Are there different milestone definitions for different project types? - What information needs to be tracked about milestones?
Note on B36: Project-based Milestone Definition - To what degree are project-specific milestones required? - Who should be able to set these up? - What information needs to be tracked?
Note on B37: Approval Tracking - How should approvals be tracked? - What information is required? - Who is responsible for tracking and recording approvals?
Note on B38: Approval Workflow - What is the approval workflow? - To what degree should this be automated? - What steps and roles are required? - Are there different approval processes for different project types?
Note on B39: Electronic Approval/Signatures - Is there a requirement for electronic signatures or approvals? - What are the requirements for obtaining approvals? - What information is required? - How are these approvals to be generated?
Note on B40: Follow-up Tracking and Management - What follow-ups are required on approvals, deferrals or declined projects? - What information is required? - What should happen if a project is deferred or declined?
Note on B42: Methodology Definition Support - What support is required for methodologies? - Do you have a methodology you want to automate? - Are you looking for a methodology as part of the solution? - What should be captured within the system? - What provisions do you require to update, maintain and customize the methodology?
Note on B43: Support for Multiple Methodologies - Do you require multiple methodologies? - What kinds of methodologies do you require support for? - Will multiple methodologies be required on a single project?
Note on B44: Methodology Adaptation for Individual Projects - Should the methodology be adaptable to specific project needs? - What kinds of exceptions are acceptable? - What controls over customization for individual projects is required?
Note on B45: Template Definition and Distribution - What template support is required? - How are templates created? - Do you use separate template documents? - Do you want full automation of template content within the portfolio management software?
Note on B46: Standard Organization Definition - What are your organizational structure and project structure requirements? - To what degree do these vary based upon portfolio or project type? - What information needs to be captured? - To what degree do these need to align to the portfolios and resource pools?
Note on B47: Role and Responsibility Definition - How should roles and responsibilities be defined? - To what extent is this integrated with the governance and resource management processes?
Note on B49: Standard Workflow Definition - To what degree are standard workflows required? - Do you need an automated workflow capability? - What workflow capabilities are required?
Note on B50: Multiple Workflow Definition Support - Do you require multiple workflows for different project types, portfolios or other segments? - To what degree do you need to be able to customize and tailor the workflow?
Note on B51: Workflow customization for Individual Projects/Portfolios - Do you need to be able to adapt workflows to the requirements of individual projects or portfolios? - Who should be able to do this? - What restrictions should be in place? C
Note on B52: Management of Individual Approvals - Are approvals granted by a single person? - Do approvals require that person to formally ‘sign off’? - Do you need an actual approval, or simply a record that the approval is in place? - What information is required? - Can approvals be delegated?
Note on B53: Management of Multiple/Group Approvals - Are there requirements for multiple or group approvals? - Are there approval hierarchies required, or specific sign-off sequences that are needed? - How should requirements for multiple signatures be managed?
Note on B54: Support for Different Approval Thresholds - Are there different approval requirements depending upon the size or type of project being conducted? - What are the dimensions that govern different approval thresholds? - How should these be reflected?
Note on B55: Approval/Role Delegation - Is it possible to delegate approval responsibilities? - Under what circumstances is this acceptable? - What are the requirement to support delegation?
Note on B57: Project Documentation Archiving - What project management information should be archived? - In what format? - Are there retention or destruction requirements? - Should these be automated or manual?
Note on B58: Project Deliverable Archiving - What project deliverables should be archived and in what format? - Are there retention or destruction requirements? - Should these be automated or manual?
Note on B59: Support for Multiple Document Types - What types of documentation are required? - What file formats should be supported?
Note on B60: Customizable Document Metadata - What information should be stored about documentation? - What fields are required? - To what degree should the fields be customizable?
Note on B61: Support for Multiple Project Categories/Portfolios - What categorization of documentation is required? - Are there categories based upon project type, customer, portfolio or organizational unit? - How should these be captured?
Note on B62: Full-text Document Search and Retrieval - Is there a requirement for full-text searches? - What information should be searchable?
Note on B64: Project plan definition - What plan information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B65: Business Case Definition - What business case information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B66: Risk Tracking - What risk tracking information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B67: Risk monitoring and management - What risk monitoring and management information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B68: Issue Tracking and Management - What issue information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B69: Scope Change Identification - What scope change request information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B70: Scope Change Impact Analysis - What scope change impact analysis information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B71: Scope Change Approval - What scope change approval information is required? - To what degree should this be able to be customized? - How should this information be captured? - What are the approval considerations?
Note on B72: Baseline Management - How should baselines be captured? - Do you require multiple baselines? - What information should be captured? - At what level of detail?
Note on B73: Cost Tracking - What cost tracking information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B74: Effort Tracking - What effort tracking information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B75: Schedule Tracking - What schedule tracking information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B76: Performance Measurement - What performance measurement data is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B77: Resource Assignment Monitoring - What resource assignment information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B78: Resource Levelling - What resource levelling capabilities are required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B79: Lessons Learned/Post Implementation Reviews - What lessons learned information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B81: Project Reporting - What are the project reporting requirements? - Do you require custom reports to be created? - Are you looking for a standard report suite? - What information should be included? - To what extent should reporting be automated? - What controls on reporting are required?
Note on B82: Portfolio Reporting - What portfolio reporting requirements are in place? - Do you require custom reports to be created? - Are you looking for a standard report suite? - What information should be included? - To what extent should reporting be automated? - What controls on reporting are required?
Note on B83: Role-based Reporting - What role-based reporting is required? - What roles require what reports? - To what extent should reporting be limited to what a person is ‘allowed’ to see? - Do you require custom reports? - Are you looking for a standard report suite? - What information should be included? - To what extent should reporting be automated? - What controls on reporting are required?
Note on B84: Standard Project Management Reports - What standard project management reports should be provided? - What format should they be created in? - How should the be accessed?
Note on B85: Standard Portfolio Reports - What standard portfolio reports should be provided? - What format should they be created in? - How should the be accessed?
Note on B86: Dashboard Portfolio Views - What dashboard views are required? - How should this information be presented? - What level of customization is required? - Who should have access to these views? - Should the information be limited to projects or portfolios they are responsible for?
Note on B87: Dashboard Project Views - What dashboard views are required? - How should this information be presented? - What level of customization is required? - Who should have access to these views? - Should the information be limited to projects or portfolios they are responsible for or involved in? - Are there different levels of detail that should be available based upon role?
Note on B88: Drill-down from Dashboards to Individual Documents/Deliverables - To what extent should dashboards enable ‘drilling down’? - To what level of detail?
Note on B89: Customization of Reports - What ability to customize reports is required? - Are there restrictions on who should be able to do this?
Note on B90: Customization of Dashboards - What ability to customize dashboards is required? - Are there restrictions on who should be able to do this?
Note on B91: Personalized Reports/Dashboards - Do people require personalized dashboards? - Should they be able to tailor and customize the information presented? - Should they have control over how the information is presented? - Should they be able to change the level of detail that is presented?
Note on B93: Analytical Tools - What analytical tools are required? - Are there restrictions on the data that should be available for analysis? - Are there restrictions on who should be able to perform analysis?
Note on B94: Decisions Support Tools - What decision support tools are required? - Are there restrictions on who should be able to use these tools?
Note on B95: Statistical and Trend Analysis Tools - What statistical and trend analysis tools are required? - What data should be available for analysis? - Are there restrictions on who should be able to perform this analysis?
Note on B97: Business Case Definition - What business case information is required? - To what degree should this be able to be customized? - How should this information be captured?
Note on B98: Business Case Change Management - To what extent should business cases be updated as circumstances change? - When should this be done? - What information is required? - Are there restrictions on who should be able to do this?
Note on B99: Performance Measurement Tracking - What performance measurement capabilities are required? - What measures should be tracked? - Do you need to be able to customize the measures that you use? - How should actual measurements be captured?
Note on B100: Value Realization Management - What are the requirements for managing value realization out of your business cases? - What information needs to be captured? - To what level of detail? - How should this information be obtained? - How will the information be used? - Are there restrictions on who should be able to capture, see or update the information?
Note on B102: Accounting - What accounting integration is required? - Is there a requirement to be able to develop financial budgets based upon your portfolios? - To update budget forecasts? - Will actual costs be imported into your portfolio management tool? - How will the integration occur? - At what level of detail will budgets and portfolios be aligned at?
Note on B103: HR Systems - What HR integration is required? - Will resources within portfolios be integrated with the HR system? - Will plan and allocation information is required by the HR system? - What security considerations exist around personnel data? - At what level of detail does integration need to occur?
Note on B104: Payroll Systems - What payroll integration is required? - Is there a need for time management information to be exported to or imported from the payroll system? - Will actual paychecks be tied to time reporting data? - What security considerations are present?
Note on B105: Work Management Systems - What work management integration is required? - Are work orders required to enable project and accounting integration? - What project and personnel information needs to be imported or exported? - At what level of detail does integration need to occur?
Note on B106: Business Planning - What business planning integration is required? - Is business plan development and tracking automated or manual? - How are business plans developed, and how will they be integrated into portfolios? - How will portfolio status translate into business plan attainment? - At what level of detail will this be managed?
Note on B107: Project Management Software - What project management integration is required? - How will current project management tools be used within portfolio management? - Will plans be created in the project management software and imported? - Will actual time and cost information be exported? - At what level of detail will integration be managed? - What control will project managers have over how integration occurs? - Who will manage updates?
Note on B108: Time Reporting - What time reporting integration is required? - How does time reporting get captured, and at what level of detail? - How will project and resource integration occur? - How will updates be managed to the portfolio management tool? - How will changes to time reporting data be reflected?
Note on B109: Analytics Engines - What analytics integration is required? - What analytical tools are currently used, and who has access to them? - What kind of data preparation or access will be required to support analytics? - Who will have access to the information? - Who will be responsible for data preparation?
Note on B110: Dashboard Reporting - What dashboard reporting integration will be required? - What level of detail will be required? - What data preparation or consolidation is necessary? - How will portfolios be aligned and reported? - What preparation is required to enable effective drill-downs of data?
Note on B111: E-mail - What email integration is required? - How will email integration be enabled? - What security provisions are required to control what can be emailed?
Note on B112: Custom Interface Capability - What custom interfaces are required? - What data is required to support the interfaces? - What data preparation is required? - Will data be accessed directly, migrated to a data warehouse, or will export files need to be created? - Who will be responsible for data preparation? - What security provisions are required?
Note on B113: XML Support - What XML support is required? - What data needs to be XML-enabled? - At what level of detail? - Who will be responsible for establishing XML formats? - What security provisions are required on how can access this?
Note on B115: Standards Support While these are not criteria per se, standards represent additional considerations that you may want to include in an evaluating of your portfolio management software requirements. To what extent do these standards create additional criteria that you need to consider in other dimensions of evaluation? * ISO 9000 * ITIL * Sarbanes-Oxley * CMMI * PMBOK
Note on B121: Stability - How stable is the vendor? - How long have they been in business? - Have they ever had financial problems? - Have they ever declared bankruptcy?
Note on B122: Revenue - What is the revenue of the vendor? - Are they too small? Too large? - Are there sufficient financial resources that they will be able to stay in business? - Do they have a sufficient revenue base to support continued product investment?
Note on B123: Installed Base - What is the installed base of software? - How many organizations use it? - How many organizations are similar to yours? - What are the experiences of other organizations in installing and adapting the software?
Note on B124: Partners - What partners does the vendor have? - Do they support integration with your other software platforms? - Are there partnership relationships that are valuable to you as an organization?
Note on B125: Support Policies - What level of support does the organization provide? - Is support included, or is it extra? - What is the response time for support? - What is the expertise of the support organization? - What are their hours of availability?
Note on B126: Warranty - What warranty provisions are provided? - What are the remedies available in the event of problems? - Is software maintenance included in the license fee? - Are maintenance costs extra?
Note on B127: Consulting Support - What consulting support is available to the organization? - What is their expertise in advising organizations on the implementation of portfolio management? - What change management expertise do they have? - What is the experience of their proposed resources in implementing similar solutions?
Note on B128: Customization Services - What customization support is required? - What is the expertise of the vendor in customizing the software? - What are the support policies for customized versions? - What are the upgrade policies and practices for customized versions?
Note on B129: Implementation Services - What are the implementation services required? - What expertise does the vendor have in supporting implementation? - What is the experience of the proposed resources? - Do they have a standard implementation methodology and training approach for the product?
Note on B130: Training Services - What training services are required? - Which stakeholders in the organization require training? - Are appropriate training programs available for all stakeholder groups? - Are standard courses provided? - What is the expertise of their training resources?
Note on B131: After-sales Support and Care - What after-sales support is required? - What commitments does the organization make to the usability of the software? - What support will they provide in ensuring the software meets your needs? - What is their commitment to upgrading and enhancing the software?
Note on B132: Escrow Policy - What are your escrow policy requirements? - Does the vendor have an escrow policy? - Under what conditions will the escrow release be triggered? - Is the escrow organization reputable and reliable?
Note on B134: Methodology - To what degree do you need to be able to tailor the methodology to your needs? - Will you use the vendor's methodology, or yours? - What methodology information should be available? - Is methodology support provided for reference, or is workflow support required?
Note on B135: Templates - To what extent do you need to have customized templates? - Will you use their templates, or yours? - Who will be responsible for updating and maintaining templates?
Note on B136: Organization Structure - To what extent do you require a customized organization structure? - Does the organization structure define the definition of portfolios, resource groups, or both? - How does the organization structure influence the project management process? - How does the organization structure influence approvals? - How stable is the organization?
Note on B137: Project Structure - To what extent do you require a customized project structure? - Will you use their structure, roles and responsibilities, or do you need to tailor the structure to your methodology?
Note on B138: Project Evaluation Criteria - To what extent do you need to be able to customize project evaluation and prioritization criteria? - Do you need to be able to customize the criteria that will be used? - Do you need different criteria for different types of projects? - How will the criteria be used?
Note on B139: Project Planning Requirements - What is the required information to support project planning? - What information will be captured, and in what format? - What level of detail is required in capturing budget, schedule and resource information? - What supporting data is required in addition to this?
Note on B140: Project Tracking - What project tracking information is required? - How will project tracking be managed? - Do you require a tool that will enable project tracking or importing of tracking information from other environments? - What level of detail do projects need to be tracked at? - What other information is required?
Note on B141: Project Reporting - What project reporting information is required? - How will project reporting be managed? - Will you use standard reports, or do you need to be able to customize them? - Who requires access to reporting information? - What security provisions are required?
Note on B142: Project Metrics - What project metrics support is required? - Will you use standard metrics, or do you need the ability to be able to customize them? - What kinds of metrics will you use? - Who will be responsible for defining and maintaining these metrics? - How will capturing of metrics information be managed? - To what level of detail?
Note on B144: Organizational Definition - What organizational information should be defined in the tool? - What information should be captured? - To what level of detail? - Where and how will this information be used?
Note on B145: Role Definition - What role information should be defined in the tool? - What information should be captured? - To what level of detail? - Where and how will this information be used?
Note on B146: Category Definition - What category information will be required? - What categories will be created, and for what purpose? - To what extent is alignment of categories required across projects, organizations and resources? - Where and how will this information be used?
Note on B147: Multiple Time Zones - What time zones does your organization operate in? - How does the tool support users who are in different time zones?
Note on B148: Multiple Currencies - What currencies does your organization operate in? - How does the tool support and manage multiple currencies? - How does it manage conversion between currencies?
Note on B149: Functional Security - What security is required in terms of who can perform what functions? - To what level of detail is this security required? - Who will be responsible for managing and updating security? - How should permissions be set up?
Note on B150: Project Security - What security is required in terms of who can access what projects? - To what level of detail is security required? - How should permissions be defined?
Note on B151: Data Security - What security is required in terms of who can access what data? - To what level of detail is security required? - How should permissions be defined?
Note on B152: Role-Based Security - What security is required in terms of what roles can access what data? - To what level of detail is security required? - How should permissions be defined?
Note on B153: Person-Based Security - What security is required in terms of specifying individual security controls on a personal exception basis? - To what level of detail is security required? - How should permissions be defined?
Note on B154: Role Delegation - To what extent should people be able to delegate their roles to others? - Under what circumstances is this required? - How should security be treated differently when a role is delegated? - Are their any restrictions on what someone who is delegated a role can do? - How should delegation be managed? - Are their controls on who can delegate their responsibilities?
Note on B155: Audit Trails - What audit trail information is required? - To what level of detail? - What events should be included in the audit trail? - Should audit trails be captured on an exception basis, or should all activities be captured?
Note on B156: Archiving - What archiving support is required? - How should archiving be managed? - What restrictions should there be on what information can be archived? - What restrictions are required on who can manage archiving? - Should information should be automatically retained? - Should archives be automatically purged after a period of time?
Note on B158: Operating System - What operating system do your servers and workstations operate on? - What operating systems must the software support?
Note on B159: Database - What database environment(s) does your organization use? - What database environments must the software support?
Note on B160: Delivery Platform - How should the software be delivered? - Should the application be installable on desktops? - Should it be delivered only through browsers? - What requirements do you have for remote access to functionality and data? - What security should be in place for people accessing data from remote locations?
Note on D5: Points 5 - Function is essential; failure to receive the capability would mean the solution is unusable. 4 - Function is highly desired; not meeting the criteria would require costly workarounds to accommodate. 3 - Function is very desired; not meeting the criteria means that some extra work would be created. 2 - Function is important; it would be inconvenient not to have the criteria met. 1 - Function is unimportant.
Note on E5: Criteria - Define the specific criteria that must be met to support the dimension. Examples could include: Dimensions 1.1.1 – Ability to identify opportunities: Criteria: Require ability to capture the request, who requested it, the degree of importance and the date the request should be completed by. Note the scoring is built into the spreadsheet. Each tool is ranked on a 1-5 scale, based upon the following criteria: Points 5 - Criteria are completely met. 4 - Criteria are mostly met; requirement can be delivered by the solution in its current form. 3 - Criteria partially met; requirement can be met with some changes to business processes. 2 - Criteria not met; requirement can be met with software customization. 1 - Criteria not met.
PRINT
PRINT PDF